## Sheet1
| Start date | End date | Duration
Optimization of machine learning model | 2021-01-03 | 2021-01-19 | 16
Increased the accuracy of the model | 2021-01-20 | 2021-02-14 | 25
Analyzed the patterns | 2021-02-15 | 2021-03-14 | 27
Gathered news to measure the volatility | 2021-03-15 | 2021-04-09 | 25
Measured the impact on supply chain | 2021-04-10 | 2021-04-20 | 6
Provide an optimized solution | 2021-04-10 | 2021-05-09 | 29
Documentation work | 2021-05-10 | 2021-05-15 | 5
44199
44331
Formulas:
End date = [Start date, row below]-1